## Slide 1: Project Reflection - RJC Data Team
Hannah Huston, Emily Manfred, Elizabeth Rhee, Manuela Roca Zapata, Mariam Jafri

## Slide 2
Sep. 25
This was our first meeting with Prof. Fox, who gave us our initial project problem - use HMDA data to support housing discrimination claims
Nov. 13
During class, we met with Prof. Kumar and worked on cleaning up our visualizations and the importance of adjusting for population as well as added in more background information about South Bend.
Sep. 9
This was the day of our initial meeting with Darryl. This is when we narrowed down the initial scope of our project and were led to the Housing Committee, as it had the most usable data.
Dec. 4
This was the date of our final presentation to Prof. Fox. We had a successful presentation where we demonstrated our research and visualization skills
Oct. 30
After we had performed initial research and visualizations, we met again with Prof. Fox and got feedback on whether our visualizations met her standards and began on fixes and our final presentation.

## Slide 3: Reflection Questions
What worked well this semester in the group?
  Our communication worked very well. We had group message that allowed us to quickly let others know what we have done, what needs to be done, what questions we had, and any reminders of deadlines.
  Additionally we were able to communicate with the leaders of a committee which allowed us to get the data we needed to create visualizations
What you should have done differently?
  During the start of the project we lost a lot of time trying to find databases by ourselves, because of this we weren’t able to start creating visualizations until late.
What were some external blockers that interrupted/disrupted your project work?
  Initially we had trouble finding the data we needed to be able to make our visualizations specially since we were trying to find information for all of the committees. Therefore, we were forced to make our main goal more obtainable and we decided to focus only on housing.
What are some good practices from the group work that you would want to keep for future projects?
  Effective communication is a must. Everyone always attended meetings and contributed in some way, but if they were not able, they let everyone on the team know, which was important so teammates were aware if they needed to help out or know that something would get done. I also liked our practice of splitting up some of the work because we cannot all code on the same document at the same time.

## Slide 4: Reflection Questions Cont.
What are some learnings from working on a real world project that you would want to remember for your future interaction with real world projects?
  Being able to make changes, adapting and adjusting is very important and something we experienced in this project. Because this project was new, there were many details that needed to be figured out in the beginning, so we mostly did research in the beginning and had to be flexible and patient with the many changes that were made to fit their needs and our abilities. We also started with a plan of splitting our team into tackling all of the subcommittee’s, but that would make us too spread out, so we ended up focusing on a single subcommittee. Working with a client was also useful because it was good practice of how to be professional as well as on time with deadlines or communicate if you cannot.
What are some skills you learned through the process of the project?
  I learned a lot about how to properly use Python in order to visualize data and how to work with large datasets. I also learned more about statistical research and how data can help to support claims in almost all circumstances.
What is the potential societal good that could be achieved when your project eventually gets implemented/deployed?
  The potential societal good that can be achieved is the ability for people in the South Bend community to be able to have fairer access to housing, as this data helps support the claim that the housing market in South Bend is unfair.